## Sheet1
S/no. | Incident/Oil Spill Ref. No. | e-Page Code | Facility/ Equipment | Facility Category | Location | Closeby Facility | Area | LGA | State | Lat (N) | Long (E) | Date of Incident/ Spill | Incident / Spill cause | Est. Qty. Spilled (bbls) | Tiered Level | Est. Qty. Recovered as at JIV (bbls) | Final qantity recovered (bbls) | JIV date | Repair date | PR Number | Date of issue | PR Value | Buyer | LOC issue date | PO issue date | Contract ref. no. | Contract value NGN | Contract value USD | Contractor name | Telephone no. | Date of kick-off meeting | Date of mobilisation | Date of monitoring/ inspection | 20% completion date | 40% completion date | 60% completion date | 80% completion date | Cleanup status | 100% completion date | Date of PCI | PCI Participants | Date of sampling | Remediation status | Date of close out request | Date of NOSDRA certificate | Is JIV invitation letter for community available? | Is Cleanup Report Available? | Is Cost assesment Available | Is SOW Available? | Is Minutes of Kick-off Meeting available? | Is Mobilization Form Available? | Is Cleanup Monitoring Form Available? | Is Community Completion Letter Available? | Remarks